## Manual Handling RA
RCS Production Risk Assessment
Manual Handling
Significant Hazard |  | Who might be Harmed? | Risk Factor (P x S) | Control Measures | Residual Risk (P x S) | Further Actions Necessary to Control Risk | Further Action Review Date:
1 | Injury from Poor Manual Handling Technique | Crew, Staff and Venues Team | 3 x 3 = 9 | All crew will have attended appropriate RCS manual handling training | 1 x 3 = 3 | Trained staff and student heads of department will supervise crew to ensure proper procedure is carried out. | Duration of Production (8th May - 9th June)
All crew will be wearing appropriate Personal Protective Equipment (PPE); steel toe capped boots, gloves etc.
Each item will be lifted by the necessary amount of crew, dependant on its weight and shape.
Wherever practical, items will be transported through use of castors or dolleys, rather than being moved by crew.
Crew will take regular breaks throughout the day to prevent fatigue.
Crew members will only lift what they feel comfortable with.
| Assessment Compiled By: | James McQueen |  |  | Date of assessment: |  | 4th May 2017
Signature:
Further Action Review:
| Position: | Deputy Technical Stage Manager |  |  | RA Review Date:
Assessment reviewed By:
Reviewer Signature:
Note: 5 x 5 Probability / Severity Matrix used

## Van Load and Unload RA
RCS Production Risk Assessment
Van Load/Unload
Significant Hazard |  | Who might be Harmed? | Risk Factor (P x S) | Control Measures | Residual Risk (P x S) | Further Actions Necessary to Control Risk | Further Action Review Date:
1 | Traffic Outside New Athanaeum Theatre Dock Door and at Speirs Lock Studios' Car Park | Crew, Staff, Client Services, Venue Techs, Visitors/General Public | 3 x 4 = 12 | All crew members will wear high-vis clothing when working on the street. | 1 x 4 = 4
Traffic cones will be put on the road to divert traffic away from the rear of the van.
Crew members will be specifically allocated to traffic watch.
2 | Injury from Poor Technique of Manual Handling | Crew, Staff, Venue Techs | 3 x 3 = 9 | All crew will have attended RCS manual handling training | 1 x 3 = 3 | Trained staff and student heads of department will supervise crew to ensure proper procedure is carried out.
All crew will be wearing appropriate Personal Protective Equipment (PPE); steel toe capped boots, gloves etc.
Each item will be lifted by the necessary amount of crew, dependant on its weight and shape.
Wherever practical, items will be transported through use of castors or dolleys, rather than being moved by crew.
Crew will take regular breaks throughout the day to prevent fatigue.
Crew members will only lift what they feel comfortable with.
3 | Slips, Trips or Falls | Crew, Staff, Venue Techs | 3 x 2 = 6 | The area where set pieces or equipment is to be stored will be cleared prior to offload, and will be kept as clear as reasonably practical. | 1 x 2 = 2
Equipment will be stacked and left in a safe manner.
| Assessment Compiled By: | James McQueen |  |  | Date of assessment: |  | 8th May 2017
Signature:
Further Action Review:
| Position: | Deputy Technical Stage Manager |  |  | RA Review Date:
Assessment reviewed By:
Reviewer Signature:
Note: 5 x 5 Probability / Severity Matrix used

## Working at Height RA
RCS Production Risk Assessment
Working at Height
Significant Hazard |  | Who might be Harmed? | Risk Factor (P x S) | Control Measures | Residual Risk (P x S) | Further Actions Necessary to Control Risk | Further Action Review Date:
1 | Falling Items from Catwalks or Tallescope | Crew, Staff, Venue Techs | 4 x 4 = 16 | Crew will have empty pockets at all times when on catwalks or in tallescope basket. | 1 x 4 = 4
Catwalks will be cleared of all loose equipment and items prior to use.
If it is necessary to take tools onto the catwalk they will be secured via a rated safety lanyard.
Orange hazard lights will be in place to alert those in the venue to any hazardous work taking place.
Those working on the ground will be wearing hard hats.
There will be a box placed SR to store any loose items whilst operator is working at height.
No unnecessary items will be taken onto catwalks or up tallescope.
2 | Falling from Height | Crew, Staff, Venue Techs | 2 x 5 = 10 | All operators will have received RCS Safe Use of Tallescope/Ladder training. | 1 x 5 = 5
Each piece of access equipment will undergo a visual inspection prior to use to check for damage.
The catwalks have been designed to prevent accidental falls.
Whilst using access equipment, manufacturers' guidelines and use recommendations will be adhered to.
3 | Slips, Trips or Falls on Catwalks | Crew | 3 x 2 = 6 | Catwalks will be kept as tidy as reasonably practical during working time. | 2 x 2 = 4
Any obstructions on catwalks will be highlighted with white tape and all loose cabling will be taped down.
| Assessment Compiled By: | James McQueen |  |  | Date of assessment: |  | 8th May 2017
Signature:
Further Action Review:
| Position: | Deputy Technical Stage Manager |  |  | RA Review Date:
Assessment reviewed By:
Reviewer Signature:
Note: 5 x 5 Probability / Severity Matrix used

## Fit Up RA
RCS Production Risk Assessment
Fit Up
Significant Hazard |  | Who might be Harmed? | Risk Factor (P x S) | Control Measures | Residual Risk (P x S) | Further Actions Necessary to Control Risk | Further Action Review Date:
1 | Injury from Poor Technique of Manual Handling | Crew, Staff, Venue Techs | 3 x 3 = 9 | All crew will have attended RCS manual handling training | 1 x 3 = 3 | Trained staff and student heads of department will supervise crew to ensure proper procedure is carried out.
All crew will be wearing appropriate Personal Protective Equipment (PPE); steel toe capped boots, gloves etc.
Each item will be lifted by the necessary amount of crew, dependant on its weight and shape.
Crew will take regular breaks throughout the day to prevent fatigue.
Crew members will only lift what they feel comfortable with.
2 | Slips, Trips or Falls | Crew, Staff, Venue Techs, Visitors | 3 x 2 = 6 | Stage area to be kept clear prior to fit up and to be kept as clear as reasonably practical. | 1 x 2 = 2
At the end of each working day, the venue will be tidied and prepared for the following day.
All trailing cables and trip hazards will be safely secured.
Areas of the venue which may be wet due to painting will be clearly signposted. Crew will be instructed to avoid these areas until they are dry.
3 | Falling Items from Catwalks or Tallescope | Crew, Staff, Venue Techs | 4 x 4 = 16 | Crew will have empty pockets at all times when on catwalks or in tallescope basket. | 1 x 4 = 4
Catwalks will be cleared of all loose equipment and items prior to use.
If it is necessary to take tools onto the catwalk they will be secured via a rated safety lanyard.
Orange hazard lights will be in place to alert those in the venue to any hazardous work taking place.
Those working on the ground will be wearing hard hats.
There will be a box placed SR to store any loose items whilst operator is working at height.
No unnecessary items will be taken onto catwalks or up tallescope.
4 | Falling from Height | Crew, Staff, Venue Techs | 2 x 5 = 10 | Each piece of access equipment will undergo a visual inspection prior to use to check for damage.
All ooperators will have received RCS Safe Use of Tallescope / Ladder training.
5 | Inhilation of Paint Fumes | Crew, Staff, Venue Techs, Visitors | 4 x 2 = 8 | Crew will take regular breaks throughout the day in order to limit exposure to fumes. | 2 x 1 = 2 | Manfacturers guidelines will be referred back to to ensure safe procedure is being followed.
The vneue will be kept well ventilated through use of air conditioning.
Appropriate PPE (particle masks) will be worn by any crew members who are exposed for lengthy periods of time.
Signs will be put on doors to alert staff and visitors to potential hazard.
6 | Use of Portable Power Tools (Battery) | Crew, Staff, Venue Techs | 2 x 4 = 8 | Only those trained ad signed off in RCS Safe Systems of Work may use power tools | 1 x 5 = 5
Each tool will undergo a visual inspection prior to use to check for damage.
The tools will be PAT tested.
Those using power tools will be wearing PPE appropriate to the tool.
| Assessment Compiled By: | James McQueen |  |  | Date of assessment: |  | 8th May 2017
Signature:
Further Action Review:
| Position: | Deputy Technical Stage Manager |  |  | RA Review Date:
Assessment reviewed By:
Reviewer Signature:
Note: 5 x 5 Probability / Severity Matrix used

## Strike RA
RCS Production Risk Assessment
Strike
Significant Hazard |  | Who might be Harmed? | Risk Factor (P x S) | Control Measures | Residual Risk (P x S) | Further Actions Necessary to Control Risk | Further Action Review Date:
1 | Injury from Poor Technique of Manual Handling | Crew, Staff, Venue Techs | 3 x 3 = 9 | All crew will have attended RCS manual handling training | 1 x 3 = 3 | Trained staff and student heads of department will supervise crew to ensure proper procedure is carried out.
All crew will be wearing appropriate Personal Protective Equipment (PPE); steel toe capped boots, gloves etc.
Each item will be lifted by the necessary amount of crew, dependent on its weight and shape.
Crew will take regular breaks throughout the day to prevent fatigue.
Crew members will only lift what they feel comfortable with.
2 | Slips, Trips or Falls | Crew, Staff, Venue Techs, Visitors | 3 x 2 = 6 | Stage area to be kept clear prior to fit up and to be kept as clear as reasonably practical. | 1 x 2 = 2
All trailing cables and trip hazards will be safely secured.
Areas of the venue which may be wet due to painting will be clearly signposted. Crew will be instructed to avoid these areas until they are dry.
3 | Falling Items from Catwalks or Tallescope | Crew, Staff, Venue Techs | 4 x 4 = 16 | Crew will have empty pockets at all times when on catwalks or in tallescope basket. | 1 x 4 = 4
Catwalks will be cleared of all loose equipment and items prior to use.
If it is necessary to take tools onto the catwalk they will be secured via a rated safety lanyard.
Orange hazard lights will be in place to alert those in the venue to any hazardous work taking place.
Those working on the ground will be wearing hard hats.
There will be a box placed SR to store any loose items whilst operator is working at height.
No unnecessary items will be taken onto catwalks or up tallescope.
4 | Falling from Height | Crew, Staff, Venue Techs | 2 x 5 = 10 | Each piece of access equipment will undergo a visual inspection prior to use to check for damage.
All operators will have received RCS Safe Use of Tallescope / Ladder training.
5 | Inhalation of Paint Fumes | Crew, Staff, Venue Techs, Visitors | 4 x 2 = 8 | Crew will take regular breaks throughout the day in order to limit exposure to fumes. | 2 x 1 = 2 | Manufacturers guidelines will be referred back to to ensure safe procedure is being followed.
The vneue will be kept well ventilated through use of air conditioning.
Appropriate PPE (particle masks) will be worn by any crew members who are exposed for lengthy periods of time.
Signs will be put on doors to alert staff and visitors to potential hazard.
6 | Use of Portable Power Tools (Battery) | Crew, Staff, Venue Techs | 2 x 4 = 8 | Only those trained ad signed off in RCS Safe Systems of Work may use power tools | 1 x 5 = 5
Each tool will undergo a visual inspection prior to use to check for damage.
The tools will be PAT tested.
Those using power tools will be wearing PPE appropriate to the tool.
| Assessment Compiled By: | James McQueen |  |  | Date of assessment: |  | 8th May 2017
Signature:
Further Action Review:
| Position: | Deputy Technical Stage Manager |  |  | RA Review Date:
Assessment reviewed By:
Reviewer Signature:
Note: 5 x 5 Probability / Severity Matrix used